## Sheet1
Government Program – PARPA |  |  | Priorities |  | Indicators | No. | PAF 2005 targets
Strategic Objectives | Areas | Sub-areas | Objectives | Actions |  |  | 2005 | Achievement (1) | Rating (2)
Poverty reduction through privileged orientation of public services to the most needy populations | Education | Primary education | Universal education: - increase access and retention - increase quality of education - reduce gender disparities | Approve, implement and assess the strategic plan for 2005-2009 - Implement the programm of low cost school construction - Implement the strategy of teachers training taking into account the new curriculum - Approve and implement the gender strategy | EP1 net enrollment rate - total | 1a | 79% | 83% | 1
[5 empty] | EP1 net enrollment rate -girls | 1b | 77% | 81% | 1
[5 empty] | EP1 completion rate - total | 2a | 43% (2004)** 48% (2005) | 48% (2004) | 1
[5 empty] | EP1 completion rate - girls | 2b | 36% (2004)** 41% (2005) | 39% (2004) | 1
| Health | Mother & Child | Maternal mortality reduced | Increase offer of obstetric care | Institutional deliveries | 3 | 49% | 49% | 1
|  |  | Infant mortality reduced | Increase coverage of the Expanded Programme on Immunization | T coverage <1 year DPT3 e HB | 4 | 95% | 94% | 3
|  |  | Increase access to basic health services | Spread access to quality treatment of transmitted and non-transmitted diseases | Utilization rate - consultations per inhabitant per year | 5 | 0.93 | 1.01 | 1
| HIV-AIDS | MISAU/ CNCS | Prevention and mitigation of the impact on people infected and affected by HIV-AIDS | Reduction of vertical transmission | # HIV+ pregnant women and neonates receiving PMTCT Prophylaxis | 6 | 15000 | 7297 | 3
|  | CNCS |  | Strengthen capacity and partnerships and spread institutional support to the programmes. | Percentage of funds channelled by CNCS-SE to CSOs and to public and private sectors (% of total funds used by CNS-SE in all types of expediture) | 7 | 55% | 60% | 1
|  |  |  | Community and home based care and support (orphans and vulnerable children) | Percentage of community initiatives or CBOs supported by CNCS-SE to support orphans and vulnerable children in the country (% of total applications of CSOs, and institutions from public and private sector) | 8 | 20% | 25% | 1
** The annual data for completion rates is available only in May, after the joint Review. For this reason, the assessment of these targets are based on data from 2004
Poverty reduction through privileged orientation of public services to the most needy populations | Infra-structures | Roads | National network improved | Rehabilitate and improve the national network | Kms. Rehabilitated | 9 | 1091 | 1 902 | 1
|  |  |  | Improve the execution of works and services | Kms Periodic Maintenance | 10 | 1635 | 1932 | 1
[5 empty] | Kms Routine Maintenance | 11 | 14343 | 11949 | 2
|  | Water | Access increased | Open well and make new connections | % Population with access to potable water | 12 | 44.2% | 40.4% | 2
|  | Sanitation | Access increased | Improved latrines, septic tanks | % Population with access to sanitation services | 13 | 37% | Nao avaliado
Promotion of economic development, with priority to the rural areas and reduction of the regional unbalances | Agriculture and Rural Development | Agricultural Services | Promotion of agricultural production | Increase coverage of agricultural outreach services | % of agricultural assisted explorations that adopted at least one new technique during the last 12 months | 14 | 28% a) 196 000 b) 3 000 000 | a) 176 729 | 2
[8 empty] | b) 2 035 101 | 2
|  |  |  | Improve coverage of animal health services | % of cattle farmers that vaccinated their livestock | 15 | 70% c) 660 000 d) 250 000 | c) 502 371 | 2
[8 empty] | d) 198 145 | 2
|  |  |  | Stimulate market mechanisms | % of cereal production (maize, sorghum and rice) commercialized by the formal sector | 16 | 16.1% | 15.6% | 1
|  |  |  | Promote use of irrigation techniques | Area (Ha) with irrigation schemes constructed and/or rehabilitated with public resources | 17 | 2900 | 2514 | 2
|  | Management of Natural Resources | Access to land | Simplify mechanisms of obtaining the rights for land tenure | % of processes received that are authorized in 90 days | 18 | 90% | 70% | 2
|  |  | Promotion of sustainable exploration of natural resources | Promote sustainable commercial management of Natural Resources through application plans | % of concessions with application plan approved | 19 | 37% | 50% | 1
a) Proxy indicator: total farmers assisted public extension services (including out-sourcing)
b) Proxy indicator: Number of vaccinations against New Castle
c) Proxy indicador: cattle vaccinated against Anthrax
d) Proxy indicador: cattle vaccinated against Black Leg
Creation of a favourable environment for private sector action | Develop private sector |  | Stimulate job creation in the formal sector, modernize commercial practice to improve economic activities, simplify the process of business registration and reduce corruption. | Amendment of the Labour Law and its submission to Parliament |  | 20 | Law submitted |  | 3
|  |  |  | Revision of the commercial code |  | 21 | Implementation (subject to Parliamentary approval) | Implementation delayed for 2006 | 3
| Macro- economic and financial policies | Financial system | Stengthen accountability in the banking sector | Conduct a financial audit of BAu commissioned through PGR |  | 22 | Finalised | Concluded | 1
|  |  | Improve financial intermediation including for micro, small, medium enterprises and households with no access to commercial banks | Institutional capacity of BoM and other regulatory authorities strengthened |  | 23 | Approval and issue of LICSF regulation | Law submitted to the Council of Ministers and regulation to be prepared | 2
|  |  |  | Implementation of strategy of BIM, including preparation of the sale of State owned shares |  | 24 | √ | Implementation to start in 2006 | 2
|  |  | Improve insurance and social protection sectors | Improvement of social protection sistem |  | 25 | Submission to Parliament of draft law on social protection | Submitted to Council of Ministers | 2
[6 empty] | 26 | Actuarial study of social security system initiated | To be transferred to 2006 | 3
Creation of a favourable environment for private sector action | Macro- economic and financial policies | Reform of the State Financial Administration System | Upgrade efficiency and effectiveness of the management of State funds | Expenditure in PARPA priority sectors is at least 65% of total expenditure excluding interest payments on debts. At least half of these 65% are related to education and health. |  | 27 | 65% | 67% (55% health and education) | 1
|  |  |  | Increase budget coverage as a requirement for programme budgeting |  | 28 | Conclude the study on off-budgets in health sector and begin implementation of the recommendations for the state budget cycle in 2006 in the health sector | Study finalised in time for 2006 cycle | 1
|  |  |  | Implement e-SISTAFE |  | 29a) | Preparation of a semi-annual budget execution report on the basis of e-SISTAFE using new budget classifiers (due 15 August 2005). | Achieved in early September 2005 | 4
[6 empty] | 29b) | Roll-out of e-SISTAFE to the Ministry of Education and Culture (MEC) will be completed by December 2005 | Roll-out of a e-SISTAFE version with a limited number of the planned functionalities to MEC | 2
|  | Tax Reform | Simpler and more covering, fair and balanced taxation | Strengthening tax administration and creation of the Revenue Authority (CRA) by 2006 |  | 30 | Approval of regulations and procedures for CRA | Approved at ministerial level but not by Cabinet, due to late approval of law by Parliament | 2
|  |  |  | Total revenue as % of GDP |  | 31 | 13.9% | 14% | 1
|  | Procurement | Adoption of a transparent and efficient system | Implement a modern procurement system in accordance with the best international practices based on the new procurement regulation and in connection with e-SISTAFE |  | 32 | Approval of a decree revising procurement regulations for public works and concessions, goods and services based on international standards in 2005. | Approved on 13 December | 1
|  | Auditing | Improve coverage and function of internal and external auditing | Implement priority components of the strategic plan in internal audit |  | 33 | √ | √ | 2
|  |  |  | Number of financial audit reports done by the Administrative Tribunal |  | 34 | 60 | 68 | 1
|  | Planning and Monitoring | Harmonization of medium and short term instruments | PARPA revision concluded through a consultation process |  | 35 | √ | √ | 4
|  |  |  | Single process of CFMP, PES and state budget formulation. |  | 36 | Start | Started | 2
Creation of a favourable environment for private sector action | Good Governance, Legality and Justice (combat corruption) | Public Sector Reform | Deconcentration and Decentralization | Prepare the decentralisation policy and strategy |  | 37 | Prepared | ToRs prepared | 3
|  |  |  | Establishment of criteria for the allocation of financial resources to districts |  | 38 | Proposed/Prepared | To be done in 2006 | 3
|  |  |  | FCA transferred to each municipality (programming and execution) and total revenue of each municipality/person (programming) |  | 39 | Value and Value/Person to be made available | No data | 3
|  |  | Rationalization of structures and processes | Government approval of the salary policy for the medium term (salary reform) and implemantation begun with the harmonization of database |  | 40 | Approval | Preparatory studies done | 3
|  |  |  | Restructuring plans agreed within MTEF and beginning of implementation in MISAU, MINED, MADER, MAE, MIC and MPD and MF |  | 41 | Plans agreed and implementation started | Plans not yet agreed and implemenation not started | 3
|  |  | Combat corruption | Conduct a survey on good governance, corruption and service delivery and implement the anti-corruption strategy |  | 42 | Strategy approved and implementation initiated | General outline of the strategy approved in 2005 by the Council of Ministers | 3
|  |  |  | Corruption survey in the justice system (proposing solutions for procedural simplification and for other causes of corruption) and recommendations implemented |  | 43 | Publication of the first study and identiication of other institutions to be included | First study concluded | 1
|  |  |  | Increase government resources (especially better recruitment of personnel) attached to the anti-corruption units |  | 44 | √ | Resources increased | 1
Consolidation of peace, national unity, justice and deomcracy | Good Governance, Legality and Justice (Fight against corruption) | Justice Reform | Increase efficiency in the provision of services by the justice system | Increase number of judicial verdicts reached (subject to change) * |  | 45 | 42% (Base year is 2002) | 149% | 1
|  |  |  | Decrease in the number of prisoners awaiting charges and trial | Maximum % of prisioners awaiting trial | 46 | 57% | 53% | 1
|  |  | Simplification and speedy judicial processes | Presentation of a long term reform program that includes a system for planning, budgeting and monitoring that prioritises service delivery in the sector | Approval of vision document by CM and revision of PEI and POPEI | 47 | √ | Little progress | 3
[5 empty] | Consolidate an harmonised M&E system based on POPEI. | 48 | √ | Little progress | 3
|  |  |  | Law reforms | Revise the Civil Process Code, | 49a) | Submission to Parliament | Submitted to Parliament | 1
[5 empty] | Revise the organic law of judicial courts including their commercial sections | 49b) | Submission to Parliament | Submitted to Parliament | 1
[5 empty] | Revise the Notary Code | 49c) | Submission to Parliament | Submitted to Parliament | 1
[5 empty] | Revise the Penal Code | 49d) | Submission to Parliament | Not submitted | 3
[5 empty] | Revise legislation on prisons | 49e) | Submission to Parliament | Not approved | 3
* See Aide memoire